## Sheet1
| Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes | Dev 1 : Nguyễn Thanh Huy
Start project | 2023-11-24 | 2023-11-24 | 100% | Dev 1 | 2023-11-24 | 2023-11-24 | 100% | Dev2 | Complete project initialization, folder structure | Dev 2 : Nguyễn Hoàng Quý
Database design | 2023-11-25 | 2023-11-25 | 100% |  | 2023-11-25 | 2023-11-25 | 100% |  | Database design
Code features and write Swagger API documentation. | 2023-11-26 | 2023-11-26 | 100% |  | 2023-11-26 | 2023-11-26 | 100% |  | Code features and write Swagger API documentation.
Code Movie Api | 2023-12-10 | 2023-12-14 |  | Dev 2 | 2023-12-14 | 2023-12-14 |  | Dev1 | Code Movie Api
Code Cinema Api | 2023-12-14 | 2023-12-17 |  |  | 2023-12-17 | 2023-12-17 |  |  | Code Movie Api